## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2024 - <Machine Learning> Project Schedule
|  | PROJECT START DATE | 2024-06-11
|  | Display Week Sr No | 1
|  | Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [11 empty] | 1899-12-31
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | S
1 | Pre Internship Program
1.1 | 1 | Completing the pre-internship program | Understanding the given materials and task of internship | NA | NA | Project Developer | 2024-06-11 | 2024-06-13 | 2024-06-13 | 3 | Completed
1.1.1 | 1 | Internship goal setting | Attending quizzes and lectures | NA | NA | Project Developer | 2024-06-11 | 2024-06-11 | 2024-06-13 | 1 | Completed
1.1.2 | 1 | Industry Training | Attending quizzes and lectures | NA | NA | Project Developer | 2024-06-12 | 2024-06-12 | 2024-06-13 | 1 | Completed
1.1.3 | 1 | Selecting live project | Choosing domain | NA | NA | Project Developer | 2024-06-13 | 2024-06-13 | 2024-06-13 | 1 | Completed
2 | Project Preparation
2.1 | 2 | Problem Statement | Understanding the problem statement | NA | NA | Project Developer | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2 | Completed
2.2 | 2 | Resource Gathering | Finding out the proper resources to use | NA | NA | Project Developer | 2024-06-15 | 2024-06-15 | 2024-06-21 | 2 | Completed
2.3 | 2 | Constructing the machine Learning model of problem statement 1 | Using python and jupyter notebook to create the project | NA | NA | Project Developer | 2024-06-14 | 2024-06-21 | 2024-06-21 | 5 | Completed
2.4 | 2 | Solving Problem Statement 2 | Calculating year of graduation | NA | NA | Project Developer | 2024-06-22 | 2024-06-24 | 2024-06-24 | 3 | Completed
3 | Project Testing
3.1 | 3 | Testing the model against different entries | Using test data file | NA | NA | Project Developer | 2024-06-25 | 2024-06-26 | 2024-06-26 | 3 | Completed
3.2 | 3 | Evaluating the model | Finding the model score | NA | NA | Project Developer | 2024-06-26 | 2024-06-26 | 2024-06-26 | 1 | Completed
4 | Project Submission
4.1 | 4 | Deliverables | Preparing the deliverables as mentioned | NA | NA | Project Developer | 2024-06-27 | 2024-06-30 | 2024-06-30 | 6 | Completed
4.2 | 4 | Submission | Submitting the project and the deliverables | NA | NA | Project Developer | 2024-07-01 | 2024-07-01 | 2024-07-01 | 1 | Completed
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you